CPs Terminal Reporting Template- Baxnaano UCT programme activities narratives

Reporting period: August- Dec 2025.

| Geographic details (AO, FMs region) | Hiran Beledweyne |  |  |
| --- | --- | --- | --- |
| CPs in the target areas | Bulaburte | FLA Timeline | 1 August 2025 – 31thDecember 2025 |
| Districts of Implementation | Buloburte | Total caseload – HHs | 4560 HHs |
| Reporting Period: Year | 2025 | Date of Report | 05th January 2026 |
| Geographic Coverage (district and number of villages covered) | 69 villages across rural areas of Bulo-burte District. | AO focal point | Abdi Adow |
| Activities – SO2 | Food-insecure people in targeted areas are better able to withstand shocks and stresses throughout the year | CP Focal Point | Mustafe Mohamud Farah |

| SECTION 1: PLEASE COMPLETE FOR ALL PROJECT ACTIVITIES |  |
| --- | --- |
| 1 | Introduction (max one pager) - Background: Area specific context analysis and rationale for the drought shock response program (stability, shock prevalence, livelihood zone, migratory patterns, socio-economic practices.ect) Geographic and Livelihood Context Buloburte District, located in central Somalia's Hiraan region, lies within an agro-pastoral livelihood zone. Communities here practice seasonal crop cultivation and livestock rearing—both highly vulnerable to climate shocks. Their primary dependence on rain-fed agriculture and small-scale pastoralism makes them acutely susceptible to droughts and floods. Although the district borders the Shabelle River, its agricultural potential remains limited due to dilapidated irrigation infrastructure, a legacy of prolonged conflict and neglect. Climate Vulnerability and Recurrent Shocks The district experiences frequent and severe climate-related shocks, primarily prolonged droughts and sudden floods. These events systematically erode household assets, disrupt food production, and trigger forced displacement. Climate change has intensified these cycles, shortening recovery periods. For example, the 2022–2023 drought caused widespread crop failure and significant livestock mortality, severely exacerbating food insecurity and malnutrition. Displacement and Migration Dynamics Environmental degradation and insecurity drive significant internal displacement in Buloburte. Families migrate seasonally or permanently in search of water, pasture, and humanitarian aid. Mobility is further restricted by the presence of Al-Shabaab, which complicates access to essential services. Many displaced persons end up in informal settlements with minimal basic amenities, deepening their dependence on external support. Stability and Humanitarian Access Buloburte is a high-risk area due to ongoing conflict and insecurity, with Al-Shabaab controlling parts of the district. This severely constrains humanitarian operations and service delivery. However, negotiated access and community-led approaches have enabled limited interventions, including cash-based assistance. This fragile context necessitates adaptable, remotely managed programs that can deliver aid without escalating risks. Socio-Economic Practices and Vulnerability Households primarily survive through subsistence farming, small-scale trade, and irregular wage labor. These seasonal and uncertain income streams are compounded by limited access to formal financial services. Women and marginalized groups face additional barriers to economic participation. The erosion of traditional coping mechanisms—like informal credit and social support networks—has heightened the vulnerability of female-headed households, the elderly, and people with disabilities. Rationale for the Baxnaano Phase Two Intervention The Baxnaano Phase Two program provided unconditional cash transfers to 4,560 impoverished and vulnerable households as a strategic response to acute, drought-induced food insecurity. This direct cash assistance allows households to meet urgent needs—such as food, water, and healthcare—while preserving dignity and stimulating local markets. By targeting the most affected communities, the intervention aims to stabilize livelihoods, reduce harmful coping strategies (e.g., asset sales, child labor), and prevent further displacement. Building Long-Term Resilience This emergency support is designed to align with and reinforce longer-term resilience-building efforts. It complements recovery initiatives focused on agricultural land restoration, climate-smart farming techniques, and community-based disaster risk reduction. The overarching goal is to restore productive capacity, enhance household resilience, and reduce the severity of future humanitarian crises, thereby fostering sustainable stability in Buloburte. |
| 2 | Methodology used to gather information reported (half page) Employing a comprehensive participatory approach, the project engaged stakeholders at every phase—from initial design and planning through to implementation, monitoring, evaluation, and reporting. This process began with the thorough identification of all key stakeholders and intended beneficiaries. Implementation commenced with broad community outreach, leading to the identification and enrollment of participants according to strict vulnerability criteria, with priority given to those most severely affected by recurrent drought. Upon enrollment, GEELO facilitated induction and orientation sessions to prepare beneficiaries. A robust monitoring system was established, featuring bi-weekly site visits and meetings conducted by GEELO field staff and community management committees. Monitoring data—including site reports and daily attendance records—was used to verify eligibility for monthly entitlements. These community committees served as vital custodians of tools and work allocation, while also resolving local issues. Environmental sustainability was a core consideration in the project’s design, ensuring minimal adverse impact. Key activities, such as the irrigated agriculture component, actively promote environmentally sound practices. GEELO is committed to eco-friendly operations and participates in local forums aimed at combating environmental degradation. By strengthening community resilience, the project not only addresses the impacts of climate change—which increasingly challenge traditional pastoralist livelihoods—but also empowers communities to manage these challenges from the grassroots level. |
| 3 | Protection: Gender Equality and Protection Mainstreaming GEELO mainstreams gender equality and protection throughout the entire project cycle. Recognizing the cultural sensitivities in Somalia, we proactively promoted the full participation of women, girls, boys, and men at all levels. Our gender strategy, it involved integrating a gender perspective into all activities, from design to evaluation. Specific measures included ensuring women's representation on community and farmers' committees to guarantee their voice in decision-making and beneficiary selection. A gender-sensitive approach was embedded in the project design, addressing discriminatory behaviors and ensuring equitable access to services for all. Commitment to Protection (PSEA) GEELO maintains a zero-tolerance policy towards Sexual Exploitation and Abuse (PSEA). All staff and partners are required to adhere to the highest standards of conduct, underpinned by regular PSEA training and contractual clauses. To ensure accountability, GEELO established a secure, user-friendly complaint mechanism, including a dedicated hotline, for safely reporting concerns. Reported incidents are managed through a strict protocol, with escalation to senior management if needed. The following actions constitute gross misconduct and are grounds for immediate dismissal: Sexual exploitation and abuse by GEELO employees or contractual workers constitute gross misconduct and, as such, are grounds for dismissal in the event of the following misconduct occurs: - Sexual activity with children (those under the age of 18) is prohibited, regardless of the age of majority or consent in the local jurisdiction. A mistaken belief about a child's age is not a defense. - It is prohibited to exchange money, employment, goods, or services for sex, including sexual favors or other forms of humiliating, degrading, or exploitative behavior. This includes the exchange of assistance owed to beneficiaries. - Sexual relationships between GEELO workers and beneficiaries are strongly discouraged due to the inherent unequal power dynamics. Such relationships jeopardize the credibility and integrity of our humanitarian assistance efforts. |
| 4 | Accountability- (Max one page). GEELO effectively puts into practice its dedication to Accountability to Affected Populations (AAP) by employing a systematic and cooperative approach that involves a diverse group of stakeholders, such as community members, local officials, project committees, and implementation partners. This methodology guarantees that the perspectives of beneficiaries play a pivotal role in the governance of the project. Our AAP approach began during project inception with comprehensive community mobilization and stakeholder sensitization meetings. These forums were essential for aligning all parties on project objectives, expectations, and implementation strategies. GEELO proactively shared detailed information on beneficiary selection criteria, entitlement packages, and the roles and responsibilities of all participants. To institutionalize transparency, we established a framework for joint Participatory Monitoring and Evaluation (PM&E), clearly defining the respective roles of GEELO staff and beneficiaries and making accountability a shared responsibility. A cornerstone of this framework has been the formation of inclusive, village-level implementation committees within every target community. Composed of project beneficiaries, these committees are empowered to participate directly in key decision-making processes, ensuring robust community ownership and oversight. GEELO actively promotes the meaningful participation of women throughout the project lifecycle, demonstrated by their significant representation on implementation committees and their assignment to influential roles across all activities. To ensure accessible and safe two-way communication, GEELO, in collaboration with WFP, established a dedicated and widely disseminated feedback and complaints hotline. This confidential channel enables beneficiaries to freely communicate feedback, lodge complaints, and share critical information, ensuring community concerns directly inform responsive project management |
| 5 | Complementary inputs(max one page) ### Organizational Profile & Area Experience The Gender Education, Empowerment & Leadership Organization (GEELO) brings over a decade of operational experience in the region, providing deep institutional knowledge of local political and social dynamics. Our established network includes focal points across the region and close working relationships with government ministries, agencies, and UN partners. ### Proven Project Portfolio GEELO has a demonstrated track record of implementing successful livelihood and resilience programs in the area: - 2020 (with FAO): Implemented Cash-for-Work and Unconditional Cash Transfer programs in Beletweyne District, alongside a Cash Plus Agriculture Input Distribution in Beletweyne/Matabaan. - 2021–2022 (with FAO): Executed a Deyr season intervention, providing Cash Plus Agricultural Inputs and Unconditional Cash Transfers to 1,850 beneficiaries in Beletweyne. This period also included a Cash Plus Livestock Input distribution, delivering 5,000 productive goats to drought-affected households. - 2020- 2025 (with WFP): implemented relief and the SNHCP/Baxnano Unconditional Cash Transfer project in Beletweyne, Buloburte, Mataban and Jalalagsi. ### Strategic Synergy & Learning All GEELO projects in the area are designed to complement one another, creating a multiplier effect that increases overall synergy, efficiency, and impact. We systematically apply lessons learned, best practices, and expertise from past projects to enhance the performance and outcomes of new initiatives. This integrated approach included cross-project collaboration on specific tasks, leveraging complementary strengths for more effective results. It also involves sharing data, research, and insights to build a comprehensive understanding of the context, leading to better-informed decision-making. ### Coordinated Stakeholder Engagement GEELO ensured a unified approach by coordinating stakeholder engagement across projects. This guarantees consistent messaging, goal alignment, and maximized collective impact. By actively identifying synergies between interventions, we foster collaboration and communication among all partners, creating a cohesive and coordinated operational framework in the area. The result is greater impact, improved efficiency, and enhanced overall performance. ### Ongoing Support: Nutrition & Vulnerability In partnership with WFP, GEELO continues to provide critical nutritional support to shield the most vulnerable from seasonal and shock-related vulnerabilities. This includes targeted preventive and therapeutic nutritional interventions for children and pregnant and lactating women (PLW). |
| 6 | Gender transformative actions The Baxnano project is founded on a gender-transformative approach—initiatives that actively challenge and reshape traditional gender norms, roles, and power dynamics to advance gender equality and empower women. This framework ensures women are not merely participants but essential leaders and agents of change. Their unique perspectives, skills, and experiences as decision-makers, organizers, and community leaders have been critical to fostering more inclusive, sustainable, and holistic project outcomes that reflect the diverse priorities of the entire community. ### Key Outcomes in Participatory Management Committees (PMCs) and Project Activities This strategic focus on gender transformation within the Baxnano project has yielded significant, measurable outcomes: 1. Enhanced Meaningful Participation: Women’s involvement moved beyond attendance to active, influential roles in decision-making, project planning, and implementation within PMCs. 2. Transformed Decision-Making Dynamics: Power and responsibilities are now shared more equally between women and men, leading to more inclusive and diverse decision-making processes that genuinely consider the needs of all community members. 3. Improved Female Representation at All Levels: From leadership positions in PMCs to active roles in field activities, women's representation increased at every project level. This ensures women's voices are not only heard but are instrumental in shaping the project’s direction and results. 4. Heightened Awareness and Agency: Project activities raised critical awareness of gender issues, empowering women to challenge stereotypes, advocate for their rights, and assume leadership roles. This has built greater self-confidence, personal agency, and capacity among female participants. 5. More Effective and Sustainable Project Outcomes: By integrating women's perspectives and skills, the project’s planning and implementation has been enriched. This has led to more effective, community-responsive solutions, enhancing the overall sustainability and impact of the intervention. |
| 7 | Reporting Program Activities (max 2 pages) - In table form give the breakdown of target groups for each activity and how many were achieved since the project begun as: - Project Objective - Providing cash transfers to targeted poor and vulnerable households and establish the key building blocks of a national shock-responsive safety net system. - Supporting households to strengthen their resilience and avoid negative coping mechanisms to meet escalating needs because of the recurring shocks in the short term. Individual target as reported. Activities; District; Planned targets; Units; Enrolled into the SPDS/SCOPE; Differences. UCT HHs; Buloburte; 4560; HHs; 4560; 0. SPDS capacity building training; Buloburte; 120; persons; 120; 0. Community engagement sessions; Buloburte; 27; sessions; 25; 2. Joint field visit; Buloburte; 1; trips; 1; 0. TOTAL. |
| 8 | Results and Impact (max 3 pages) 1. Beneficiary Enrollment and Case Management In Buloburte district, the project successfully enrolled 4,560 households. A detailed case management process identified 25 households with specific, complex needs. Of these, 25 cases were unresolved through targeted interventions. 2. Collaborative Security and Stability Initiatives. GEELO contributed to enhanced security and stability in Buloburte district through proactive, collective initiatives. We facilitated collaboration between a diverse range of stakeholders, including government authorities, international agencies, religious leaders, and community elders. This coordinated effort has been instrumental in maintaining peace, resulting in a notably more stable and secure operating environment for humanitarian and development activities. 3. Coordination and Mainstreaming of Protection GEELO actively participates in the district's monthly GBV coordination meetings. These forums serve as a critical platform for discussing GBV-related issues, sharing information, and developing collaborative strategies to address cases and advance the goals of the GBV cluster. Furthermore, our field team maintains close working relationships with regional and district leaders, village committees, youth organizations, women's groups, and environmental activists. Through these partnerships, we conduct ongoing sensitization and ensure the mainstreaming of protection principles for all Baxnaano program beneficiaries. 4. Accountability Systems: Complaints and Feedback Mechanism (CFM) In line with our core commitment to accountability, GEELO established a formal Complaints and Feedback Mechanism (CFM) in September 2025. This mechanism provides a safe, accessible, and confidential channel for Persons of Concern (POCs) to request information, provide feedback, and lodge complaints regarding project services. The CFM is a vital tool for promoting transparency and ensuring community concerns are heard and addressed, creating a direct feedback loop between beneficiaries and service providers. 5. Robust Monitoring and Evaluation Framework The project implemented a responsive Monitoring and Evaluation (M&E) system, aligned with the Somali National Humanitarian Coordination Platform (SNHCP) results framework. This comprehensive strategy included regular monthly monitoring visits to all project sites. Field teams utilized pre-set monitoring tools to systematically assess project performance against established targets, enabling data-driven decision-making and ensuring programmatic accountability. |
| 9 | Stakeholder Feedback (max 3 pages) Effective coordination, facilitated by the World Food Programme (WFP) in its role as the Food Security Cluster lead, was a cornerstone of the project's success. GEELO worked in close partnership with humanitarian agencies, government authorities, and community stakeholders to ensure programmatic complementarity, eliminate duplication of efforts, and maximize collective impact and operational efficiency. This collaborative framework was operationalized through regular joint planning sessions, performance review meetings, and coordinated field visits, which fostered a culture of continuous reporting, monitoring, and mutual learning. #### Contextual Adaptability and Multi-Sectoral Reach To navigate the complex and volatile operating environment in Buloburte—characterized by persistent forced evictions, insurgent activities, and clan-based land disputes—the project was designed with inherent flexibility. Interventions remained fluid and dynamic, allowing for real-time modifications in targeting and implementation to respond to population movements and shifting contextual dynamics. This adaptive management approach ensured the project remained relevant and effective in achieving its core objectives. Consequently, a multi-sectoral approach was employed, designed to be applicable across various locations within Buloburte to address the interconnected needs of the population. #### Partnerships for Enhanced Accountability and Impact GEELO embedded itself within the local ecosystem of governance and aid coordination. We engaged deeply with community structures, including traditional and religious leadership, and actively participated in all relevant humanitarian clusters. Furthermore, a strong partnership was established with all pertinent line ministries, who provided invaluable technical support and independent monitoring, significantly enhancing the quality and accountability of program delivery. #### Collaboration with Local Governance The local administration and respective municipalities were integral partners, participating in regular coordination and review meetings. Their direct involvement and oversight were critical in aligning the project with local priorities and contributed substantially to improved project performance and community buy-in. |
|  | Challenges and Lessons Learned (max one page) 1. Logistical & Operational Challenges - Systemic Delays in Communication: Unreliable network infrastructure and fragmented processes caused significant delays in sending SMS alerts to beneficiaries. These delays created a cascade effect, leading to implementation setbacks, beneficiary confusion, and a compressed timeline for subsequent activities. - Inaccurate or Outdated Data: Incomplete or outdated community data hindered accurate targeting and registration. This risked the exclusion of eligible beneficiaries, the inclusion of ineligible individuals, and community disputes, undermining the project's credibility and fairness. - Logistical Constraints in Insecure Areas: Physical access to remote or conflict-affected villages was frequently restricted by poor road conditions, seasonal floods, and active security threats. This impeded the delivery of assistance, effective monitoring, and direct communication with communities. 2. Community & Social Dynamics - Unrealistic Community Expectations: A lack of prior humanitarian assistance in the area, combined with immense need, led some community members to develop expectations exceeding the project's defined scope. This resulted in frustration, perceptions of unfairness, and tension between beneficiaries and staff. - Power Dynamics and Elite Capture: Influential community leaders or powerful individuals sometimes attempted to manipulate the beneficiary selection process to divert resources to their own networks, bypassing the most vulnerable households. - Protection Risks at Distribution Sites: Overcrowding and inadequate crowd management exacerbated protection risks for vulnerable groups—particularly women, children, the elderly, and persons with disabilities—who faced increased risks of harassment or harm in chaotic environments. 3. Security & Contextual Challenges - Direct Security Threats: The ongoing presence and activity of non-state armed groups posed a direct threat to staff, beneficiaries, and project assets. This necessitated constant risk assessments, forced last-minute cancellations of activities, and increased operational costs for security measures. #### Key Lessons Learned - Proactive Communication and Transparency are Foundational: Unrealistic expectations largely stem from inadequate initial communication. Future projects must prioritize clear, early, and repeated messaging via all available channels to articulate the project scope, selection criteria, timelines, and limitations. This upfront transparency is crucial for managing expectations, building trust, and preventing frustration. - Design for Mobility and Dynamic Contexts: Project cycles must be explicitly designed around the seasonal mobility patterns of agro-pastoralist communities. Our initial timeline failed to fully account for migration as a core survival strategy, leading to difficulties in locating displaced beneficiaries. Future planning must integrate flexible timelines and adaptive tracking methods to ensure assistance reaches the most vulnerable, even as they move. - Strengthen Feedback Loops for Accountability: A formal feedback mechanism is essential but insufficient if not actively promoted, trusted, and responsive. Establishing and robustly managing a two-way communication channel is critical for proactive problem-solving, reinforcing accountability, and strengthening stakeholder relationships. - Prioritize Protection through Meticulous Planning: Overcrowding at distribution points is a preventable protection failure. Future interventions require a pre-determined crowd management plan, including separate queues for vulnerable groups, scheduled time slots, and adequate trained staff and security to ensure the safety and dignity of all participants. - Scale is a Critical Component of Impact: The profound level of vulnerability in the area underscores the need to scale assistance. Communities have explicitly requested expanded livelihood opportunities. Increasing beneficiary caseloads where feasible is necessary to meet pressing needs and contribute meaningfully to sustainable development. |
| 10 | Sustainability and Future Recommendations (max 1 page) ### Sustainable Impact and the Humanitarian-Development Nexus This project has successfully established a replicable model for transitioning vulnerable households from emergency dependency toward resilience and self-sustainability. Designed from its inception with a clear exit strategy, the intervention integrated long-term measures to address food security gaps that would persist beyond the project's conclusion. The initiative’s primary outcome is the significantly improved livelihood security of 4,560 households across 69 villages in Buloburte district. To ensure this impact is durable, the project moved beyond meeting immediate food and nutrition needs by actively advising and encouraging beneficiaries to establish savings practices. This crucial step provides a financial buffer and serves as a foundation for developing independent livelihood sources after the project ends. ### Post-Implementation Follow-Up and Learning To solidify this transition, GEELO, in partnership with other agencies, conducts regular post-implementation follow-ups with beneficiaries. This continued engagement focuses on providing guidance to reinforce their gains and navigate emerging challenges, moving beyond material aid. A critical operational insight from this phase was the inefficiency caused by multiple organizations implementing separate projects for the same beneficiary pool within a single area. To maximize impact and resource use, GEELO strongly recommends enhanced coordination at the cluster level to prevent duplication of effort and ensure a more coherent, complementary approach in future interventions. ### Recommendations for Future Action The humanitarian context in Hirshabelle remains severe, with critically high levels of vulnerability. The cumulative impact of consecutive poor rainfall seasons and persistent drought is expected to further deteriorate livelihoods, food security, and nutrition outcomes. In direct response to this acute need and consistent community appeals, we propose the following priorities for future programming: - Expansion of Assistance Caseloads: Future interventions must scale up to match the magnitude of the need, supporting a greater number of vulnerable households. - Diversification of Livelihood Opportunities: There is an urgent, community-identified demand for programs that create diverse and sustainable income sources to combat high unemployment and limited economic options in the region. |
| 9 | Annexes (share relevant documents) Annex 1: Gallery photos (photos with original format and not cropped ones, insert proper names) Annex 2: Additional data tables and charts. # Overall progress to date (Numbers) Total caseload UCT; 4560 HHs. Enrolments progress; 4560 HHs. Case management; 25 HHs. Beneficiaries didn’t show-up; 0 HHs. Tentative completion date:; 31thDecember 2025. Annex 3: Any other relevant documents or supplementary information (PDM reports, Joint field visits reports) |

Thanks for your contribution towards attaining the zero-hunger goal.